## Sheet1
사용자 유형 | 주제 ID | 주제명 | 에픽 ID | 에픽명 | 스토리 ID | 스토리 | 중요도 | 우선순위 | 추정 작업량 | 진도
Customer | T01 | User Management | E01 | Acount Creation | ST_0101 | As a customer, creating acount to use application's services. | High |  | 5pts
Customer | T01 | User Management | E01 | Acount Creation | ST-0102 | If customer need to change their password, they must authentificate themselves. | High |  | 3pts
Admin | T01 | User Management | E02 | Acount Verification | ST-0201 | Admin verificates new users to identify if they are bots. | Medium |  | 3pts
Customer | T01 | User Management | E03 | Sign In | ST-0301 | If acount is created successfully, customer signs in. | High |  | 3pts
Customer | T02 | Data Processing | E04 | Uploading | ST-0401 | Customer uploads their files(PDF, PPT, Word...). | High |  | 3pts
System | T02 | Data Processing | E05 | Parsing | ST-0501 | System examinates and processes the file. | High |  | 2pts
System | T02 | Data Processing | E06 | Image Processing | ST-0601 | System extracts the images and verifies it. | Low |  | 3pts
System | T03 | Lecture Examinating | E07 | Lecture Summarizing | ST-0701 | System summarizes the lecture and contents. | High |  | 3pts
System | T03 | Lecture Examinating | E07 | Lecture Summarizing | ST-0702 | System presents the keyword. | Medium |  | 1pts
System | T03 | Lecture Examinating | E08 | Test Making | ST-0801 | System makes some types of test and displays it to User. | Medium |  | 4pts
Customer | T03 | Lecture Examinating | E09 | Soving | ST-0901 | User solves the problem that system made from lectures. | Medium |  | 1pts
System | T03 | Lecture Examinating | E10 | Grading | ST-1001 | System grades user's level and ability | Low |  | 1pts
System | T04 | User Schedule Management | E11 | Scheduling | ST-1101 | System understands that how much User can do and makes learning schedule | Medium |  | 1pts